## TASK
task_code | status_code | wbs_id | task_name | start_date | end_date | primary_base_start_date | primary_base_end_date | complete_pct | target_cost | bcws | bcwp | act_cost | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | (*)Start | (*)Finish | (*)BL1 Start | (*)BL1 Finish | Activity % Complete(%) | (*)Budgeted Total Cost(£) | (*)Planned Value Cost(£) | (*)Earned Value Cost(£) | (*)Actual Total Cost(£) | Delete This Row
A1000 | Completed | KX-P8.1.1 | Monthly Progress Report & Meeting | 2026-01-01 08:00 | 2026-01-01 08:00 | 2026-01-01 08:00 | 2026-01-01 08:00 | 100 | 0 | 0 | 0 | 0
A1010 | Not Started | KX-P8.1.2 | Process Final Account | 2026-09-28 08:00 | 2026-10-09 16:00 | 2026-07-20 08:00 | 2026-07-31 16:00 | 0 | 0 | 0 | 0 | 0
A2000 | Completed | KX-P8.2.1 | Mobilise Design Team | 2026-01-01 08:00 | 2026-01-01 16:00 | 2026-01-01 08:00 | 2026-01-01 16:00 | 100 | 0 | 0 | 0 | 0
A2010 | Completed | KX-P8.2.1 | Issue "For Construction" Foundation Designs | 2026-01-02 08:00 | 2026-01-29 16:00 | 2026-01-02 08:00 | 2026-01-29 16:00 | 100 | 0 | 0 | 0 | 0
A2020 | Completed | KX-P8.2.2 | Issue "For Construction" M&E/Comms Designs | 2026-01-02 08:00 | 2026-02-05 16:00 | 2026-01-02 08:00 | 2026-02-05 16:00 | 100 | 0 | 0 | 0 | 0
A3000 | Completed | KX-P8.3.1 | Tender and Appoint Piling Subcontractor | 2026-01-16 08:00 | 2026-02-26 16:00 | 2026-01-16 08:00 | 2026-02-26 16:00 | 100 | 0 | 0 | 0 | 0
A3010 | Completed | KX-P8.3.2 | Place Order for DfMA Platform Sections | 2026-01-30 08:00 | 2026-02-05 16:00 | 2026-01-30 08:00 | 2026-02-05 16:00 | 100 | 0 | 0 | 0 | 0
A3020 | In Progress | KX-P8.3.2 | Manufacture & Deliver DfMA Sections (80 units) | 2026-02-06 08:00 | 2026-05-05 12:00 | 2026-02-06 08:00 | 2026-02-12 16:00 | 50 | 0 | 0 | 0 | 0
A3030 | Not Started | KX-P8.3.3 | Procure Long-Lead M&E (CCTV, PIS, OPO) | 2026-05-01 08:00 | 2026-07-23 16:00 | 2026-02-06 08:00 | 2026-04-30 16:00 | 0 | 0 | 0 | 0 | 0
A4000 | Completed | KX-P8.4.1 | Set Up Site Welfare & Offices | 2026-01-01 08:00 | 2026-01-14 16:00 | 2026-01-01 08:00 | 2026-01-14 16:00 | 100 | 0 | 0 | 0 | 0
A4010 | Completed | KX-P8.4.2 | Install Site Hoarding & Access Gates | 2026-01-15 08:00 | 2026-01-21 16:00 | 2026-01-15 08:00 | 2026-01-21 16:00 | 100 | 0 | 0 | 0 | 0
A5000 | Completed | KX-P8.5.1 | Mark Out & Scan for Services (Pre-Possession) | 2026-01-22 08:00 | 2026-01-28 16:00 | 2026-01-22 08:00 | 2026-01-28 16:00 | 100 | 0 | 0 | 0 | 0
A5010 | Completed | KX-P8.5.1 | (POSSESSION) - Demolish Existing Platform (250m) | 2026-01-29 08:00 | 2026-02-25 16:00 | 2026-01-29 08:00 | 2026-02-25 16:00 | 100 | 150000 | 150000 | 150000 | 0
A5020 | In Progress | KX-P8.5.2 | (POSSESSION) - Install Micro-pile Foundations (Zone 1) | 2026-02-27 08:00 | 2026-05-20 16:00 | 2026-02-27 08:00 | 2026-03-19 16:00 | 6.67 | 125000 | 125000 | 8333.33 | 0
A5030 | Not Started | KX-P8.5.2 | (POSSESSION) - Install Micro-pile Foundations (Zone 2) | 2026-05-21 08:00 | 2026-06-10 16:00 | 2026-03-20 08:00 | 2026-04-09 16:00 | 0 | 125000 | 125000 | 0 | 0
A5040 | Not Started | KX-P8.5.2 | (POSSESSION) - Install Micro-pile Foundations (Zone 3) | 2026-06-11 08:00 | 2026-07-01 16:00 | 2026-04-10 08:00 | 2026-04-30 16:00 | 0 | 125000 | 125000 | 0 | 0
A5050 | Not Started | KX-P8.5.3 | (POSSESSION) - Install DfMA Sections (Zone 1) | 2026-05-21 08:00 | 2026-06-03 16:00 | 2026-03-20 08:00 | 2026-04-02 16:00 | 0 | 250000 | 250000 | 0 | 0
A5060 | Not Started | KX-P8.5.3 | (POSSESSION) - Install DfMA Sections (Zone 2) | 2026-06-11 08:00 | 2026-06-24 16:00 | 2026-04-10 08:00 | 2026-04-23 16:00 | 0 | 250000 | 250000 | 0 | 0
A5070 | Not Started | KX-P8.5.3 | (POSSESSION) - Install DfMA Sections (Zone 3) | 2026-07-02 08:00 | 2026-07-15 16:00 | 2026-05-01 08:00 | 2026-05-14 16:00 | 0 | 250000 | 0 | 0 | 0
A5080 | Not Started | KX-P8.5.4 | Install Drainage & Form Troughs (Zone 1-3) | 2026-06-25 08:00 | 2026-07-15 16:00 | 2026-04-24 08:00 | 2026-05-14 16:00 | 0 | 80000 | 26666.67 | 0 | 0
A5090 | Not Started | KX-P8.5.4 | Install Platform Surfacing & Tactile Paving | 2026-07-24 08:00 | 2026-08-20 16:00 | 2026-05-15 08:00 | 2026-06-11 16:00 | 0 | 110000 | 0 | 0 | 0
A5100 | Not Started | KX-P8.5.5 | M&E First Fix (Cabling, Containment) | 2026-06-25 08:00 | 2026-07-15 16:00 | 2026-04-24 08:00 | 2026-05-14 16:00 | 0 | 75000 | 25000 | 0 | 0
A5110 | Not Started | KX-P8.5.5 | M&E Second Fix (Install CCTV, PIS, PA, OPO) | 2026-07-24 08:00 | 2026-08-20 16:00 | 2026-05-15 08:00 | 2026-06-11 16:00 | 0 | 90000 | 0 | 0 | 0
A5120 | Not Started | KX-P8.5.5 | M&E Power & Comms Connections | 2026-08-21 08:00 | 2026-09-03 16:00 | 2026-06-12 08:00 | 2026-06-25 16:00 | 0 | 45000 | 0 | 0 | 0
A6000 | Not Started | KX-P8.6.1 | Test and Commission all M&E/Comms Systems | 2026-09-04 08:00 | 2026-09-17 16:00 | 2026-06-26 08:00 | 2026-07-09 16:00 | 0 | 50000 | 0 | 0 | 0
A6010 | Not Started | KX-P8.6.2 | Client Walk-down & Snagging | 2026-09-18 08:00 | 2026-09-24 16:00 | 2026-07-10 08:00 | 2026-07-16 16:00 | 0 | 0 | 0 | 0 | 0
A6020 | Not Started | KX-P8.6.2 | Project Handover | 2026-09-25 08:00 | 2026-09-25 16:00 | 2026-07-17 08:00 | 2026-07-17 16:00 | 0 | 0 | 0 | 0 | 0
M1000 | Not Started | KX-P8.7.1 | MILESTONE: Contract Start | 2026-05-01 08:00 |  | 2026-01-01 08:00 |  | 0 | 0 | 0 | 0 | 0
M1010 | Not Started | KX-P8.7.1 | MILESTONE: Platform Closed to Public | 2026-05-01 08:00 |  | 2026-02-02 08:00 |  | 0 | 0 | 0 | 0 | 0
M1020 | Not Started | KX-P8.7.1 | MILESTONE: Platform Demolition Complete |  | 2026-05-01 08:00 |  | 2026-02-25 16:00 | 0 | 0 | 0 | 0 | 0
M1030 | Not Started | KX-P8.7.1 | MILESTONE: Platform Structure Complete |  | 2026-07-15 16:00 |  | 2026-05-14 16:00 | 0 | 0 | 0 | 0 | 0
M1040 | Not Started | KX-P8.7.1 | MILESTONE: Ready for Passenger Service |  | 2026-09-25 16:00 |  | 2026-07-17 16:00 | 0 | 0 | 0 | 0 | 0

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd/MM/yyyy CurrencyFormat=Pound Sterling